PSH: Guides Selecting a CMO
V1.0 – SEPTEMBER 2026

# Service Provider Comparison and Ranking Scorecards

Use these tables to compare providers consistently. Agree the weighting before responses are reviewed, then score each provider against the same criteria.

Weighting guidance

Set weightings before reviewing responses. Use a simple 1–5 weighting scale where 1 = low importance, 3 = important and 5 = critical. Score each provider separately using the same scale, then multiply weight by score to support a balanced comparison.

| Process | Suggested weighting focus | Guidance |
| --- | --- | --- |
| RFI | Capability, fit, compliance status, capacity and engagement. | Use RFI weightings to decide who should be shortlisted, not who should be awarded the work. Avoid over-weighting cost at this stage unless budget fit is a firm constraint. |
| RFP | Technical approach, quality/regulatory fit, timeline realism, risk management and commercial transparency. | Use RFP weightings to test delivery confidence. Cost should be considered, but not allowed to outweigh technical, quality or timeline risk unless that reflects the agreed project priorities. |

If a criterion is a true must-have, treat failure against it as a stop/go issue rather than a low score. Weightings should reflect the project milestone, not a generic view of what matters.

RFI comparison and ranking scorecard

| Criteria | What to compare | Weight | Score | Evidence/ notes |
| --- | --- | --- | --- | --- |
| Capability fit | Can the provider perform the required service, technology, dosage form or activity? |  |  |  |
| Relevant experience | Has the provider worked on similar products, stages, scales or technical challenges? |  |  |  |
| GMP, licence and compliance fit | Does the provider appear to have the right quality status, licences and regulatory experience? |  |  |  |
| Capacity and timing | Is there likely capacity within the required timeframe? |  |  |  |
| Handling and facility fit | Can the provider manage containment, safety, storage, cold chain or specialist handling needs? |  |  |  |
| Strategic fit | Does the provider type match the outsourcing strategy? |  |  |  |
| Commercial fit | Does the provider meet the commercial expectations in terms of: |  |  |  |
|  | COGs |  |  |  |
|  | Target cost per saleable unit |  |  |  |
|  | Batch size |  |  |  |
|  | Markets |  |  |  |
|  | Annual forecast volumes |  |  |  |
|  | Maximum cost-to-serve |  |  |  |
| Quality of response | Was the response clear, relevant, factual and specific rather than generic? |  |  |  |
| Engagement and problem solving | Did the provider ask useful questions, identify risks and explain how gaps would be managed? |  |  |  |
| Decision | Shortlist for RFP, hold for later, or remove from consideration. |  |  |  |

RFP comparison and ranking scorecard

| Criteria | What to compare | Weight | Score | Evidence/ notes |
| --- | --- | --- | --- | --- |
| Technical approach | Is the proposed approach suitable, realistic and aligned to the project milestone? |  |  |  |
| Scope and deliverables | Are the deliverables clear, complete and consistent with what was requested? |  |  |  |
| Assumptions and exclusions | Are assumptions, exclusions, dependencies and sponsor responsibilities clearly stated? |  |  |  |
| Quality and regulatory fit | Does the proposal meet GMP, documentation, release, licence and regulatory expectations? |  |  |  |
| Analytical and technical depth | Are analytical, formulation, process, stability, packaging and release needs properly addressed? |  |  |  |
| Timeline realism | Is the timeline credible, with clear dependencies, decision points and lead times? |  |  |  |
| Resource and project management | Is there a credible team, governance model, communication route and escalation process? |  |  |  |
| Risk management | Has the provider identified key technical, quality, supply chain, timeline and commercial risks? |  |  |  |
| Commercial transparency | Are pricing, payment assumptions, optional costs, change controls and exclusions clear? |  |  |  |
| Capacity and continuity | Can the provider support the work now and beyond (future scalability)? |  |  |  |
| Communication and responsiveness | Has the provider been clear, timely and constructive during clarification? |  |  |  |
| Overall fit | Does the provider balance technical fit, delivery confidence, quality, cost and working style? |  |  |  |
| Total Delivered Cost | Factoring in all potential costs, not solely manufacturing |  |  |  |
| Decision | Preferred provider, reserve provider, further clarification needed, or remove from consideration. |  |  |  |